Risk Register Template

InspectionReport.app — Project Risk Management

Project: Main Street Commercial Building — Dublin

Prepared By: _______________

Date: _______________

Last Review Date: _______________

| Risk ID | Risk Description | Category | Likelihood (1-5) | Impact (1-5) | Risk Score (L×I) | Existing Controls / Mitigation | Further Actions | Owner | Status | Target Date | Review Date |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R-001 | Worker fall from scaffolding during facade installation | Safety | 4 | 5 | 20 | Full guardrails installed; harness points provided; weekly inspection of scaffolding | Install additional toe boards at all working levels; conduct refresher training | Site Manager | Open | 15/08/2026 | 01/08/2026 |
| R-002 | Excavation trench collapse near public footpath | Safety | 3 | 5 | 15 | Trench box used for all excavations >1.2m; battering at 45°; daily inspection by competent person | Install pedestrian barriers along entire trench length; add shoring at section B | Site Engineer | Open | 01/08/2026 | 25/07/2026 |
| R-003 | Crane overturn during steel beam lifting | Safety | 2 | 5 | 10 | Crane operator CPCS certified; lift plan approved; outriggers on spreader plates; exclusion zone established | Conduct additional wind-speed monitoring; revise lift plan for beam sections >8t | Lifting Supervisor | Open | 10/08/2026 | 28/07/2026 |
| R-004 | Fire from hot works (welding/cutting) on upper floors | Safety | 3 | 4 | 12 | Hot work permit system; fire watch assigned; extinguishers within 10m; combustible materials cleared | Add dedicated fire watch for each hot work crew; install temporary fire alarms on floors 3-5 | Fire Marshal | Open | 05/08/2026 | 25/07/2026 |
| R-005 | Structural overloading during concrete pour on suspended slab | Structural | 2 | 4 | 8 | Pour sequence specified in method statement; striking times calculated; shores in place per design | Monitor pour rate with real-time load cells on critical props; increase propping under bay 4 | Structural Engineer | Open | 12/08/2026 | 28/07/2026 |
| R-006 | Strike of underground gas main during service duct excavation | Utility | 3 | 4 | 12 | CAT scan & utility survey completed; hand-dig trial holes at known crossing points | Extend CAT scan to cover entire service route; mark all known utilities with spray paint | Site Manager | Open | 20/07/2026 | 15/07/2026 |
| R-007 | Dust exposure (respirable silica) from concrete cutting | Health | 4 | 3 | 12 | Water suppression on all saws; RPE (FFP3) mandatory in cutting zones; air monitoring weekly | Install local exhaust ventilation (LEV) in basement cutting area; provide half-face respirators | HSE Officer | Open | 01/08/2026 | 25/07/2026 |
| R-008 | Unauthorised access to site by public / children | Security | 3 | 3 | 9 | 2.4m hoarding around site; locked gates; security patrol 18:00-06:00; warning signs posted | Install CCTV covering east gate and rear fence; reinforce hoarding panel at section C | Security Manager | In Progress | 25/07/2026 | 20/07/2026 |

Risk Scoring Legend

■  Low (1-4) — Acceptable     ■  Medium (5-9) — Tolerable     ■  High (10-15) — Substantial     ■  Critical (16-25) — Intolerable

Status Key

Open — Risk identified, no action taken yet

In Progress — Mitigation actions underway

Closed — Risk fully mitigated / accepted

Monitoring — Controls in place, ongoing observation

Additional Entries

| Risk ID | Risk Description | Category | Likelihood (1-5) | Impact (1-5) | Risk Score (L×I) | Existing Controls / Mitigation | Further Actions | Owner | Status | Target Date | Review Date |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |